May 2002

Annual Progress Report

to the

Global Alliance for Vaccines and Immunization (GAVI)

and

The Vaccine Fund

by the Government of

Azerbaijan

Date of submission: September 27, 2002 Reporting period: September 26,2001- September 26, 2002 ( Tick only one ) : Inception report ( First annual progress report ( Financial sustainability plan attached ( Second annual progress report ( Third annual progress report ( Fourth annual progress report ( Fifth annual progress report (

# Progress Report

(Number of children immunized with current and new vaccines is collected from the WHO/UNICEF Joint Reporting Form (JRF))

To be filled in by the country for each type of support received from GAVI/The Vaccine Fund.

BCG-98%: DPT3-98%: Pol3-99%; Measles-99%;

## Immunization Services

#### 1.1.1	Receipt of immunization services funding                          Date(s) of receipt of funds…………..

The amount of US $16495 provided by GAVI/ The Vaccine Fund  was received on March 17, 2001.

The amount of US $16497 provided by GAVI/ The Vaccine Fund  was received on January,22,2002.

The amount of US $99997 provided by GAVI/ The Vaccine Fund  was received on February, 07, 2001.

Please report on the progress, including any problems that have been encountered with regard to support for immunization strengthening.  Please describe the mechanism for management of these funds, including the role of the Inter-Agency Co-ordinating Committee (ICC).

There have not been encountered any problems with regard to support immunization strengthening. Inter-regional trainings had been provided with covering all districts of Azerbaijan.. Education materials had been prepared for Health care providers.  IEC materials had been prepared for health care providers and for population. For strengthen cold chain system had been procured 42 refrigerators and 22 generators. The introduction of Hep B vaccine into the National EPI calendar had been successfully implemented since October , 2001. Allocation and management of these funds were discussed on regular ICC meetings.

#### 1.1.2	Statement on use of GAVI/The Vaccine Fund immunization services support

In the past year, the following major areas of activities have been funded with the GAVI/The Vaccine Fund contribution.

| Area of immunization services support | Total amount in US $ | Proportion of funds by level |
| --- | --- | --- |
|  |  | Central | District | Service delivery |
| Vaccines |  |  |  |  |
| Injection supplies |  |  |  |  |
| Personnel |  |  |  |  |
| Transportation |  |  |  |  |
| Maintenance and overheads |  |  |  |  |
| Training | 12930 |  | 12930 |  |
| IEC / social mobilization | 3070 |  | 3070 |  |
| Monitoring and surveillance | 3100 |  |  | 3100 |
| Vehicles |  |  |  |  |
| Cold chain equipment | 13323 |  |  | 13323 |
| Other …………. ( currency exchange operations) | 74 | 74 |  |  |

Please indicate the date(s) of the ICC meeting(s) when the allocation of funds was discussed : ……………………….

Allocation of the 1st tranche (the amount of US $ 16495) was discussed on the 28 December 2001 year.

Allocation of the 2nd tranche (the amount of US $ 16497) was discussed on the 15 February  2002 year

Allocation of the 3rd tranche (the amount of US $ 99997) was discussed on the 19 April, and 16 September 2002 year

#### Immunization Data Quality Audit (DQA) (If it has been implemented in your country)

#### N/A

A plan of action to improve the reporting system based on the recommendations from the DQA, has been prepared

## YES                              NO

The plan of action has been discussed and endorsed by the ICC in the meeting of ………………………(Date).

## New & Under-used Vaccines

#### 1.2.1	Receipt of new and under-used vaccines		Date(s) of receipt of vaccines 20 June 2002

Please report on the progress, including starting date of vaccinations and any problems that have been encountered with regard to vaccines and supplies provided by GAVI/The Vaccine Fund.

## 280000 doses of hepatitis B vaccine (in 10 doses vials) for the amount US$ 86800 have been received in Azerbaijan on 20 June 2002

In addition , 338000 pcs of syringes  and 3750 pcs of safety boxes have been delivered later.

Vaccination on Hep B had been started from October 2001. 17545 children was vaccinated with Hep B2(98.6%) in2001 and  17500 children was vaccinated  with Hep B3 in the 1st six months of the 2002 year.

#### 1.2.2	Major activities

Please outline what major activities have been or will be undertaken to prepare for new vaccine introduction.

The introduction of Hepatitis B  into the National EPI calendar  had been successfully implemented. Trainings in 42 districts on EPI and introduction on Hep B had been conducted. For social mobilization purpose , posters and leaflets and other IEC materials reflecting new vaccine in the EPI were produced and distributed according to the work plan. In order to strengthen safety of Hep B immunization cold chain equipments procured.

#### 1.2.3	Statement on use of GAVI/The Vaccine Fund financial support (US$100,000) for the introduction of the new vaccine

The following major areas of activities have been funded (specify the amount in US$) with the GAVI/The Vaccine Fund support:

To date these funds have not been spent. But Allocation of this fund  (Table 1) was discussed in the ICC meeting.

## Table1

# Allocation Of  GAVI/Vaccine Fund Financial Support (US$ 100.000)

| Area of support | Amount in US$ | Level of support |
| --- | --- | --- |
|  |  | Central | District |
| 1.Syringes BCG- 100.000 Syringes 0.5gr-400.000 | 10.000 42.000 |  | 10.000 42.000 |
| 2 Apparatus for elimination of contaminated materials 10 | 12.000 | 12.000 |  |
| Cold chain equipment Refrigerators- Generators- Thermobags | 20.900 |  | 20.900 |
| 4. Transport for carrying load | 10.000 | 10.000 |  |
| 5. Monitoring and supervision -Test preparation and reproduction 300$ Travel expenses: 30 District for 3 days 1 person 160 $ 1 district 4800$-30 districts | 5.100 | 5100 |  |
| Total 100.000$ |

## Injection safety

#### 1.3.1	Receipt of injection safety support (N/A)

Please report on the progress, including any problems that have been encountered with regard to the injection safety support.

#### Progress of transition plan for safe injections and safe management of sharps waste.

Should include objectives, indicators, main achievements, main constraints and targets for next year.

#### 1.3.3	Statement on use of GAVI/The Vaccine Fund injection safety support (if received in the form of a cash contribution)

The following major areas of activities have been funded (specify the amount) with the GAVI/The Vaccine Fund injection safety support in the past year:

# 2.  Financial sustainability

Inception Report :		Outline steps towards the development of a financial sustainability plan

First Annual Report : 	Submit completed financial sustainability plan

Subsequent Reports :	Summarize progress on financial sustainability

The Government is committed to procure vaccines from the end of first quarter of 2003.

# 3.	Request for new and under-used vaccines for year   2003 ( indicate forthcoming year )

  - Up-dated immunization targets

Confirm/update basic data (= surviving infants, DTP3 targets, New vaccination targets) of the multi-year immunization plan approved with country application: revised Table 4 of approved application form and give reasons for any changes.

| Table 1 : Baseline and annual targets |
| --- |
| Number of | Baseline and targets |
|  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 |
| Births |  | 111655 | 112771 | 113898 | 115036 | 116186 |  |  |
| Infants’ deaths |  | 3270 | 3292 | 3324 | 3357 | 3390 |  |  |
| Surviving infants |  | 108386 | 109470 | 110565 | 111671 | 112788 |  |  |
| Infants vaccinated with DTP3 * |  | 80205 | 82152 | 84789 | 87103 | 90229 |  |  |
| Infants vaccinated with *Hep B(use one row for any new vaccine) |  | 40645 | 87576 | 93980 | 100504 | 10509 |  |  |
| Wastage rate of ** Hep B |  | 25% | 20% | 15% | 10% | 10% |  |  |

* Indicate actual number of children vaccinated in past years

** Indicate actual wastage rate obtained in past years

If the request for supply for the coming years differs from previously approved plan:

Please indicate the reasons for those changes and, where relevant, the related modifications of targets of children to be vaccinated, wastage rate and type of vaccine. Indicate that UNICEF Supply Division has assured the availability of the new quantity of supply according to new changes. Summarise the related modifications of the activities and of the budgets of the work-plan for introduction of new vaccines and indicate the date of the ICC meeting when the changes were endorsed.

3.2	Confirmed/revised request for new vaccine (to be shared with UNICEF Supply Division) for the year …2003… (indicate forthcoming year)

Table 2: Estimated number of doses of …Hep B… vaccine (specify for one presentation only) : (Please repeat this table for any other vaccine presentation requested from

GAVI/The Vaccine Fund

|  |  | Formula | For year 2003 | Remarks |
| --- | --- | --- | --- | --- |
| A | Number of children to receive new vaccine |  | 93980 | Phasing: Please adjust estimates of target number of children to receive new vaccines, if a phased introduction is intended. If targets for hep B3 and Hib3 differ from DTP3, explanation of the difference should be provided Wastage of vaccines: The country would aim for a maximum wastage rate of 25% for the first year with a plan to gradually reduce it to 15% by the third year. For vaccine in single or two-dose vials the maximum wastage allowance is 5%. No maximum limits have been set for yellow fever vaccine in multi-dose vials. Buffer stock: The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero under other years. In case of a phased introduction with the buffer stock spread over several years, the formula should read: [ F – number of doses (incl. wastage) received in previous year ] * 0.25. Anticipated vaccines in stock at start of year… ….: It is calculated by deducting the buffer stock received in previous years from the current balance of vaccines in stock. AD syringes: A wastage factor of 1.11 is applied to the total number of vaccine doses requested from the Fund, excluding the wastage of vaccines. Reconstitution syringes: it applies only for lyophilized vaccines. Write zero for other vaccines. Safety boxes: A multiplying factor of 1.11 is applied to safety boxes to cater for areas where one box will be used for less than 100 syringes |
| B | Percentage of vaccines requested from The Vaccine Fund | % | 100 |  |
| C | Number of doses per child |  | 3 |  |
| D | Number of doses | A x B/100 x C | 281940 |  |
| E | Estimated wastage factor | (see list in table 3) | 1.18 |  |
| F | Number of doses ( incl. wastage) | A x C x E x B/100 | 332689 |  |
| G | Vaccines buffer stock | F x 0.25 | 83172 |  |
| H | Anticipated vaccines in stock at start of year …. |  | 130000 |  |
| I | Total vaccine doses requested | F + G - H | 285861 |  |
| J | Number of doses per vial |  | 70%-10 dose 30%-2 dose |  |
| K | Number of AD syringes (+ 10% wastage) | ( D + G – H ) x 1.11 | 390844 |  |
| L | Reconstitution syringes (+ 10% wastage) | I / J x 1.11 | ---- |  |
| M | Total of safety boxes (+ 10% of extra need) | ( K + L ) / 100 x 1.11 | 4338 |  |

Table 3 : Wastage rates and factors

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2.00 | 2.22 | 2.50 |

#### 3.3	Confirmed/revised request for injection safety support

(If quantity of current request differs from the GAVI letter of approval, please present the justification for that difference).

Table 4.1: Estimated supplies for safety of vaccination for the next two years with BCG (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4.1 to 4.4)

|  |  | Formula | For year 2003 | For year 2004 |
| --- | --- | --- | --- | --- |
| A | Target of children for BCG vaccination | # | 109342 | 111585 |
| B | Number of doses per child | # | 1 | 1 |
| C | Number of BCG doses | A x B | 109342 | 111585 |
| D | AD syringes (+10% wastage) | C x 1.11 | 121370 | 123860 |
| E | AD syringes buffer stock | D x 0.25 | 30342 | 0 |
| F | Total AD syringes | D + E | 151712 | 123859 |
| G | Number of doses per vial | # | 20 | 20 |
| H | Vaccine wastage factor | Either 2 or 1.6 | 2 | 2 |
| I | Number of reconstitution syringes (+10% wastage) | C x H x 1.11 / G | 12137 | 12386 |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 1819 | 1512 |

Table 4.2: Estimated supplies for safety of vaccination for the next two years with DTP (Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4.1 to 4.4)

|  |  | Formula | For year 2003 | For year 2004 |
| --- | --- | --- | --- | --- |
| A | Target of children for DTP vaccination | # | 84789 | 87103 |
| B | Number of doses per child | # | 3 | 3 |
| C | Number of DTP doses | A x B | 254367 | 261309 |
| D | AD syringes (+10% wastage) | C x 1.11 | 282347 | 290053 |
| E | AD syringes buffer stock | D x 0.25 | 70587 | 0 |
| F | Total AD syringes | D + E | 352934 | 290053 |
| G | Number of doses per vial | # | 10 | 10 |
| H | Vaccine wastage factor | Either 2 or 1.6 | 1.6 | 1.6 |
| I | Number of reconstitution syringes (+10% wastage) | C x H x 1.11 / G | 0 | 0 |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 3918 | 3220 |

Table 4.1: Estimated supplies for safety of vaccination for the next two years with Measles(Use one table for each vaccine BCG, DTP, measles and TT, and number them from 4.1 to 4.4)

|  |  | Formula | For year 2003 | For year 2004 |
| --- | --- | --- | --- | --- |
| A | Target of children for Measles vaccination | # | 78391 | 80291 |
| B | Number of doses per child | # | 1 | 1 |
| C | Number of Measles doses | A x B | 78391 | 80291 |
| D | AD syringes (+10% wastage) | C x 1.11 | 87014 | 89123 |
| E | AD syringes buffer stock | D x 0.25 | 21754 | 0 |
| F | Total AD syringes | D + E | 108768 | 89123 |
| G | Number of doses per vial | # | 10 | 10 |
| H | Vaccine wastage factor | Either 2 or 1.6 | 1.6 | 1.6 |
| I | Number of reconstitution syringes (+10% wastage) | C x H x 1.11 / G | 13922 | 14260 |
| J | Number of safety boxes (+10% of extra need) | ( F + I ) x 1.11 / 100 | 1362 | 1148 |
| Table 5: Summary of total supplies for safety of vaccinations with BCG, DTP, TT and measles for the next two years. |
| ITEM | For the year 2003 | For the year 2004 | Justification of changes from originally approved supply: |
| Total AD syringes | for BCG | 151712 | 123859 |  |
|  | for other vaccines | 461702 | 379176 |  |
| Total of reconstitution syringes | 26059 | 26646 |  |
| Total of safety boxes | 7099 | 5880 |  |

# Signatures

For the Government of .Azerbaijan

Signature:	……………………………………………...……………...

Title:	… Abbas Valibayov Deputy Minister of Health……………

Date:	……………27 September,2002…………………………….………………….

We, the undersigned members of the Inter-Agency Co-ordinating Committee endorse this report. Signature of endorsement of this document does not imply any financial (or legal) commitment on the part of the partner agency or individual.

Financial accountability forms an integral part of GAVI/The Vaccine Fund monitoring of reporting of country performance.  It is based on the regular government audit requirements as detailed in the Banking form.  The ICC Members confirm that the funds received have been audited and accounted for according to standard government or partner requirements.

| Agency/Organisation | Name/Title | Date Signature | Agency/Organisation | Name/Title | Date Signature |
| --- | --- | --- | --- | --- | --- |
| RCHE | Zmitrovich S. P. Deputy Director EP coordinator | 27 September,2002 (signed) | WHO | Abdullayev F. Liaison Officer | 27 September,2002 (signed |
| RCHE | Huseynov F.Z/General Director | 27 September,2002 (signed | UNICEF | Abdullayeva A. EPI Officer | 27 September,2002 (signed |
| MOH | Mehdiyeva. K. ICC Secretary | 27 September,2002 (signed | IFRC | Jabbarova A. Health Officer | 27 September,2002 (signed |
| RIP | Kuliyev N. Director | 27 September,2002 (signed | Mercy Corps | Radmilla Mirzayeva | 27 September,2002 (signed |
| RCHE | Aliyev. N. Director, Supply Division | 27 September,2002 (signed |  |  |  |

# Footnotes

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, 1.6 for measles and YF.

Only for lyophilized vaccines. Write zero for other vaccines

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, 1.6 for measles and YF.

Only for lyophilized vaccines. Write zero for other vaccines

The buffer stock for vaccines and AD syringes is set at 25%. This is added to the first stock of doses required to introduce the vaccination in any given geographic area. Write zero for other years.

Standard wastage factor will be used for calculation of re-constitution syringes. It will be 2 for BCG, 1.6 for measles and YF.

Only for lyophilized vaccines. Write zero for other vaccines

# Text boxes

Partnering with The Vaccine Fund